## Slide 1: Construction Operation
Ferdinand Fassa
Lecture 8

## Slide 2: Outline
Authority and Responsibility of all Parties
Time of Inspection and Test
Contractor Submittals
Instruction to field
Suspension or Termination of The Work

## Slide 3: 1. Authority and Responsibility of all Parties
Owner
  Authorized to award contract
  To make changes in the work
  To withhold payments from the contractor for adequate cause
  To inspect the work as progresses
  To direct contractor to expedite the work
  To make payment deductions from incomplete or faulty work

## Slide 4: 1. Authority and Responsibility of all Parties
Contractor
  Major responsibility is to construct the project in accordance with the drawings, specification, and other contract documents.
Resident Project Representative
  Inspect the workmanship, materials, and manner of construction of all building and appurtenant structures.

## Slide 5: 2. Time of Inspection and Test
Contractor must give the engineer timely notice
Tests and inspections required by public agencies must usuaslly be paid for by the contractor
Test and inspections, other than those mentioned, that are required by the contract document will be paid for by the owner
Extra inspection required as the result of a deficiency noted by the inspector must be paid for by the contractor
The contractor firm must provide all materials for testing at its own cost and expense

## Slide 6: 3. Contractor Submittals
All submittals from the contractor should be handled in a systematic, consistent, and orderly manner.
Contractor submittals are to be documented both when coming in going out
Keep photographic records of progress and all potential claim issue
Contractor submittal handled only through Resident Project Representative

## Slide 7: 4. Instruction to field
Inspect the work as it progress
No field changes without Project Manager Instruction
Instruction to the contractor through superintendent or Project Manager
Field orders and change orders must be handled through Resident Project Representative

## Slide 8: 4. Instruction to field
No changes on oral instructions without written confirmation
No significant deviations from plans and specifications except by change order-event if no cost or time extension is involved
Emergency changes by work directive change followed latter by a change order

## Slide 9: 5. Suspension or Termination of The Work
Suspension of work by the Owner
Termination

## Slide 10: Question